## Copyright
Copyright
# Planning-Template.xlsx Copyright (C) 2012-2026 Rafael Corchuelo. In keeping with the traditional purpose of furthering education and research, it is the policy of the copyright owner to permit non-commercial use and redistribution of this software. It has been tested carefully, but it is not guaranteed for any particular purposes. The copyright owner does not offer any warranties or representations, nor do they accept any liabilities with respect to them.
REVISAR EL NÚMERO DE ENTREGAS ESTE CURSO!!!!!
La columna estatus es redundante con Execution Period. Poner autocalculada.
Poner filtros en las columnas.

## Abstract
Abstract
This spreadsheet is intended to facilitate planning on the tasks of your project. Please, share it in your workgroup and closely follow the methodology taught.
Help comments
Enter configuration data in these cells
Warning and error messages.
Data computed automatically. Do not change them.
Internal data. Do not change them.

## D01
Deliverable D01
Use this form to document the tasks that you perform in your projects. Please, review the colour code in the "Abstract" sheet. In the exceptional case that you need to perform more tasks than expected, add them at the end.
| Costs | Expected: | 4957.5
|  | Actual: | 5399
[7 empty] | Execution period |  |  | Workload (in hours) |  | Costs (in EUR)
ORDER | ID | Type | Assignee | Role | Activity | Parent | Start moment | End moment | Status | Expected | Actual | Expected | Actual | Description
1 | T0001/O | Other | ALL | Student | Attend lecture |  | 2026-01-26 10:40 | 2026-01-26 12:30 | Completed | 1.8333 | 1.83 | 0 | 0 | L01 – Introduction, S01 – The subject
2 | T0002/O | Other | ALL | Student | Attend lecture |  | 2026-01-29 08:30 | 2026-01-29 10:40 | Completed | 1.8333 | 1.8333 | 0 | 0 | L01 – Introduction, S02 – Working together
3 | T0003/O | Other | ALL | Student | Attend lecture |  | 2026-02-02 10:40 | 2026-02-02 12:30 | Completed | 1.8333 | 1.83 | 0 | 0 | L01 – Introduction, S03 – Getting started
4 | T0004/O | Other | ALL | Student | Attend lecture |  | 2026-02-05 08:30 | 2026-02-05 10:40 | Completed | 1.8333 | 1.83 | 0 | 0 | L01 – Introduction, S04 – The framework
5 | T0005/O | Other | ALL | Student | Attend lecture |  | 2026-02-09 10:40 | 2026-02-09 12:30 | Completed | 1.8333 | 1.83 | 0 | 0 | Follow up
6 | T0006/O | Other | ALL | Student | Attend lecture |  | 2026-02-12 08:30 | 2026-02-12 10:40 | Completed | 1.8333 | 1.83 | 0 | 0 | L02 – The data model, S01 – Models and queries
7 | T0007/O | Other | ALL | Student | Attend lecture |  | 2026-02-16 10:40 | 2026-02-16 12:30 | Completed | 1.8333 | 1.83 | 0 | 0 | Follow up
8 | T0008/O | Other | ALL | Student | Attend lecture |  | 2026-02-19 08:30 | 2026-02-19 10:40 | Completed | 1.8333 | 1.83 | 0 | 0 | L02 – The data model, S02 – Validation and population
9 | T0009/O | Other | ALL | Student | Attend lecture |  | 2026-02-23 10:40 | 2026-02-23 12:30 | Completed | 1.8333 | 1.83 | 0 | 0 | Follow up
10 | T0010/O | Other | ALL | Student | Attend lecture |  | 2026-02-26 08:30 | 2026-02-26 10:40 | Completed | 1.8333 | 1.83 | 0 | 0 | L02 – The data model, S03 – Advanced topics
11 | T0011/O | Other | ALL | Student | Attend lecture |  | 2026-03-02 10:40 | 2026-03-02 12:30 | Completed | 1.8333 | 1.83 | 0 | 0 | Follow up
12 | T0012/O | Other | ALL | Student | Attend lecture |  | 2026-03-05 08:30 | 2026-03-05 10:40 | Completed | 1.8333 | 1.83 | 0 | 0 | L03 – Implementing features, S01 – Display features
13 | T0013/O | Other | ALL | Student | Attend lecture |  | 2026-03-09 10:40 | 2026-03-09 12:30 | Completed | 1.8333 | 1.83 | 0 | 0 | Follow up
14 | T0014/O | Other | ALL | Student | Attend lecture |  | 2026-03-12 08:30 | 2026-03-12 10:40 | Completed | 1.8333 | 1.83 | 0 | 0 | L03 – Implementing features, S02 – Edition features
15 | T0015/O | Other | ALL | Student | Attend lecture |  | 2026-03-16 10:40 | 2026-03-16 12:30 | Completed | 1.8333 | 1.83 | 0 | 0 | Follow up
16 | T0016/O | Other | ALL | Student | Attend lecture |  | 2026-03-19 08:30 | 2026-03-19 10:40 | Completed | 1.8333 | 1.83 | 0 | 0 | L03 – Implementing features, S03 – Advanced topics
17 | T0017/O | Other | ALL | Student | Attend lecture |  | 2026-03-23 10:40 | 2026-03-23 12:30 | Completed | 1.8333 | 1.83 | 0 | 0 | Assessments
18 | T0018/O | Other | ALL | Student | Attend lecture |  | 2026-03-26 08:30 | 2026-03-26 10:40 | Completed | 1.8333 | 1.83 | 0 | 0 | Assessments
19 | T0019/M | Management | Student 1 | Manager | Other (Describe) |  | 2026-01-26 12:30 | 2026-01-26 13:30 | Completed | 1 | 1 | 50 | 50 | Setup Clockify Workspace
20 | T0020/M | Management | Student 1 | Manager | Write report |  | 2026-01-27 13:30 | 2026-01-27 16:30 | Completed | 2 | 3 | 100 | 150 | Chartering report
21 | T0021/M | Management | Student 1 | Manager | Make plans |  | 2026-01-26 13:30 | 2026-01-26 16:30 | Completed | 2 | 3 | 100 | 150 | Assign tasks: Hello-World instantiation and Sample Data
22 | T0022/M | Management | Student 1 | Manager | Make plans |  | 2026-01-26 17:00 | 2026-01-26 17:30 | Completed | 3 | 0.5 | 150 | 25 | Instantiate and share planning document for D01
23 | T0023/M | Management | Student 1 | Manager | Make plans |  | 2026-01-29 10:40 | 2026-01-29 11:30 | Completed | 2 | 0.83 | 100 | 41.5 | Assign workers for Model-CG.ufx constraints implementation
24 | T0024/M | Management | Student 1 | Manager | Supervise task |  | 2026-01-30 10:00 | 2026-03-26 12:30 | Completed | 20 | 10 | 1000 | 500 | Supervise sample data creation (admin credentials check)
25 | T0025/M | Management | Student 1 | Manager | Supervise task |  | 2026-02-02 | 2026-02-16 12:30 | Completed | 15 | 4.5 | 750 | 225 | Supervise implementation of Model-CG constraints
26 | T0026/M | Management | Student 1 | Manager | Make plans |  | 2026-01-29 17:30 | 2026-01-29 18:00 | Completed | 1 | 1 | 50 | 50 | Assign different project customization tasks for every worker
27 | T0027/M | Management | Student 1 | Manager | Supervise task |  | 2026-02-05 08:30 | 2026-02-05 21:30 | Completed | 1 | 1 | 50 | 50 | Supervise project customization tasks
28 | T0028/D | Development | Student 1 | Developer | Customise the starter |  | 2026-02-05 09:30 | 2026-02-05 10:00 | Completed | 0.5 | 0.5 | 12.5 | 12.5 | Edit Changelog.txt, Footer fragments and Welcome messages
29 | T0029/D | Development | Student 1 | Analyst | Create domain model |  | 2026-02-05 10:00 | 2026-02-15 10:00 | Completed | 2 | 4 | 80 | 160 | Implement data model sketched in Model-C01.uxf
30 | T0030/D | Development | Student 1 | Developer | Implement feature |  | 2026-02-10 18:00 | 2026-02-10 23:30 | Completed | 2 | 5.5 | 50 | 137.5 | Functional: Acquire inventor role and update profile
31 | T0031/QA/T0030/D | QA | Student 1 | Developer | Test feature informally | T0030/D | 2026-02-16 17:30 | 2026-02-23 11:00 | Completed | 1 | 2 | 25 | 50 | Produce sample data for 3 inventor accounts
32 | T0032/QA/T0030/D | QA | Student 1 | Tester | Test feature formally | T0030/D | 2026-02-23 11:00 | 2026-02-23 11:30 | Completed | 0.5 | 0.5 | 15 | 15
33 | T0033/D | Development | Student 1 | Developer | Implement feature |  | 2026-02-16 | 2026-03-19 | Completed | 2 | 3.5 | 50 | 87.5 | Functional: List/display published inventions and parts
34 | T0034/QA/T0033/D | QA | Student 1 | Developer | Test feature informally | T0033/D | 2026-03-19 17:00 | 2026-03-19 18:00 | Completed | 1 | 2 | 25 | 50
35 | T0035/QA/T0033/D | QA | Student 1 | Tester | Test feature formally | T0033/D | 2026-03-19 18:00 | 2026-03-19 19:00 | Completed | 1 | 1 | 30 | 30
36 | T0036/D | Development | Student 1 | Developer | Implement feature |  | 2026-02-28 19:00 | 2026-03-11 13:00 | Completed | 2 | 4 | 50 | 100 | Functional: Manage (CRUD) inventions and parts
37 | T0037/QA/T0036/D | QA | Student 1 | Developer | Test feature informally | T0036/D | 2026-03-11 13:00 | 2026-03-11 14:00 | Completed | 1 | 1 | 25 | 25
38 | T0038/QA/T0036/D | QA | Student 1 | Tester | Test feature formally | T0036/D | 2026-03-11 14:00 | 2026-03-11 15:00 | Completed | 1 | 1 | 30 | 30
39 | T0039/D | Development | Student 1 | Developer | Implement feature |  | 2026-03-11 16:30 | 2026-03-15 12:00 | Completed | 2 | 3 | 50 | 75 | Functional: Publish invention
40 | T0040/QA/T0039/D | QA | Student 1 | Developer | Test feature informally | T0039/D | 2026-03-15 12:00 | 2026-03-15 13:00 | Completed | 1 | 1 | 25 | 25
41 | T0041/QA/T0039/D | QA | Student 1 | Tester | Test feature formally | T0039/D | 2026-03-15 13:00 | 2026-03-15 14:00 | Completed | 1 | 1 | 30 | 30 | Formal testing of invention publishing and inventor workflows
42 | T0042/D | Development | Student 1 | Developer | Customise the starter |  | 2026-03-19 19:00 | 2026-03-19 20:30 | Completed | 1.5 | 1.5 | 37.5 | 37.5 | UI Internationalisation (EN/ES) for inventions-related views
43 | T0043/D | Development | Student 2 | Developer | Customise the starter |  | 2026-02-05 09:30 | 2026-02-05 10:00 | Completed | 0.5 | 0.5 | 12.5 | 12.5 | Edit Readme.txt and Favicon.ico
44 | T0044/D | Development | Student 2 | Analyst | Create domain model |  | 2026-02-05 10:00 | 2026-02-15 10:00 | Completed | 2 | 4 | 80 | 160 | Implement data model sketched in Model-C02.uxf
45 | T0045/D | Development | Student 2 | Developer | Implement feature |  | 2026-02-10 18:00 | 2026-02-10 23:30 | Completed | 2 | 5.5 | 50 | 137.5 | Functional: Acquire spokesperson role and update profile
46 | T0046/QA/T0045/D | QA | Student 2 | Developer | Test feature informally | T0045/D | 2026-02-16 17:30 | 2026-02-23 11:00 | Completed | 1 | 2 | 25 | 50 | Create sample data for 3 spokesperson accounts
47 | T0047/QA/T0045/D | QA | Student 2 | Tester | Test feature formally | T0045/D | 2026-02-23 11:00 | 2026-02-23 11:30 | Completed | 0.5 | 0.5 | 15 | 15
48 | T0048/D | Development | Student 2 | Developer | Implement feature |  | 2026-02-16 | 2026-03-19 | Completed | 2 | 3.5 | 50 | 87.5 | Functional: List and display published campaigns and milestones
49 | T0049/D | Development | Student 2 | Developer | Test feature informally | T0048/D | 2026-03-19 17:00 | 2026-03-19 18:00 | Completed | 1 | 1 | 25 | 25
50 | T0050/QA/T0048/D | QA | Student 2 | Tester | Test feature formally | T0048/D | 2026-03-19 18:00 | 2026-03-19 19:00 | Completed | 1 | 1 | 30 | 30
51 | T0051/D | Development | Student 2 | Developer | Implement feature |  | 2026-02-28 19:00 | 2026-03-11 13:00 | Completed | 2 | 4 | 50 | 100 | Functional: CRUD for campaigns and milestones (as spokesperson)
52 | T0052/D | Development | Student 2 | Developer | Test feature informally | T0051/D | 2026-03-11 13:00 | 2026-03-11 14:00 | Completed | 1 | 1 | 25 | 25
53 | T0053/QA/T0051/D | QA | Student 2 | Tester | Test feature formally | T0051/D | 2026-03-11 14:00 | 2026-03-11 15:00 | Completed | 1 | 1 | 30 | 30
54 | T0054/D | Development | Student 2 | Developer | Implement feature |  | 2026-03-11 16:30 | 2026-03-15 12:00 | Completed | 2 | 3 | 50 | 75 | Functional: Campaign publishing and immutability logic
55 | T0055/D | Development | Student 2 | Developer | Test feature informally | T0054/D | 2026-03-15 12:00 | 2026-03-15 13:00 | Completed | 1 | 1 | 25 | 25
56 | T0056/QA/T0054/D | QA | Student 2 | Tester | Test feature formally | T0054/D | 2026-03-15 13:00 | 2026-03-15 14:00 | Completed | 1 | 1 | 30 | 30 | Formal testing of campaign publishing and spokesperson workflows
57 | T0057/D | Development | Student 2 | Developer | Customise the starter |  | 2026-03-19 19:00 | 2026-03-19 20:30 | Completed | 1.5 | 1.5 | 37.5 | 37.5 | UI Internationalisation (EN/ES) for campaign-related views
58 | T0058/D | Development | Student 3 | Developer | Customise the starter |  | 2026-02-05 09:30 | 2026-02-05 10:00 | Completed | 0.5 | 0.5 | 12.5 | 12.5 | Edit Banner.png and Banner fragments
59 | T0059/D | Development | Student 3 | Analyst | Create domain model |  | 2026-02-05 10:00 | 2026-02-15 10:00 | Completed | 2 | 4 | 80 | 160 | Implement data model sketched in Model-C03.uxf
60 | T0060/D | Development | Student 3 | Developer | Implement feature |  | 2026-02-10 18:00 | 2026-02-10 23:30 | Completed | 2 | 5.5 | 50 | 137.5 | Functional: Acquire fundraiser role and update profile
61 | T0061/D | Development | Student 3 | Developer | Test feature informally | T0060/D | 2026-02-16 17:30 | 2026-02-23 11:00 | Completed | 1 | 2 | 25 | 50 | Create sample data for 3 fundraiser accounts
62 | T0062/QA/T0060/D | QA | Student 3 | Tester | Test feature formally | T0060/D | 2026-02-23 11:00 | 2026-02-23 11:30 | Completed | 0.5 | 0.5 | 15 | 15
63 | T0063/D | Development | Student 3 | Developer | Implement feature |  | 2026-02-16 | 2026-03-19 | Completed | 2 | 3.5 | 50 | 87.5 | Functional: List and display published strategies and tactics
64 | T0064/D | Development | Student 3 | Developer | Test feature informally | T0063/D | 2026-03-19 17:00 | 2026-03-19 18:00 | Completed | 1 | 1 | 25 | 25
65 | T0065/QA/T0063/D | QA | Student 3 | Tester | Test feature formally | T0063/D | 2026-03-19 18:00 | 2026-03-19 19:00 | Completed | 1 | 1 | 30 | 30
66 | T0066/D | Development | Student 3 | Developer | Implement feature |  | 2026-02-28 19:00 | 2026-03-11 13:00 | Completed | 2 | 4 | 50 | 100 | Functional: CRUD for strategies and tactics
67 | T0067/D | Development | Student 3 | Developer | Test feature informally | T0066/D | 2026-03-11 13:00 | 2026-03-11 14:00 | Completed | 1 | 1 | 25 | 25
68 | T0068/QA/T0066/D | QA | Student 3 | Tester | Test feature formally | T0066/D | 2026-03-11 14:00 | 2026-03-11 15:00 | Completed | 1 | 1 | 30 | 30
69 | T0069/D | Development | Student 3 | Developer | Implement feature |  | 2026-03-11 16:30 | 2026-03-15 12:00 | Completed | 2 | 3 | 50 | 75 | Logic for publishing strategies and immutability
70 | T0070/D | Development | Student 3 | Developer | Test feature informally | T0069/D | 2026-03-15 12:00 | 2026-03-15 13:00 | Completed | 1 | 1 | 25 | 25
71 | T0071/QA/T0069/D | QA | Student 3 | Tester | Test feature formally | T0069/D | 2026-03-15 13:00 | 2026-03-15 14:00 | Completed | 1 | 1 | 30 | 30 | Formal testing of strategy publishing and fundraiser workflows
72 | T0072/D | Development | Student 3 | Developer | Customise the starter |  | 2026-03-19 19:00 | 2026-03-19 20:30 | Completed | 1.5 | 1.5 | 37.5 | 37.5 | UI Internationalisation (EN/ES) for strategy-related views
73 | T0073/D | Development | Student 4 | Developer | Customise the starter |  | 2026-02-05 09:30 | 2026-02-05 10:00 | Completed | 0.5 | 0.5 | 12.5 | 12.5 | Edit Banner.txt and Company fragments
74 | T0074/D | Development | Student 4 | Analyst | Create domain model |  | 2026-02-05 10:00 | 2026-02-15 10:00 | Completed | 2 | 4 | 80 | 160 | Implement data model sketched in Model-C04.uxf
75 | T0075/D | Development | Student 4 | Developer | Implement feature |  | 2026-02-10 18:00 | 2026-02-10 23:30 | Completed | 2 | 5.5 | 50 | 137.5 | Functional: Acquire sponsor role and update profile
76 | T0076/D | Development | Student 4 | Developer | Test feature informally | T0075/D | 2026-02-16 17:30 | 2026-02-23 11:00 | Completed | 1 | 2 | 25 | 50 | Create sample data for 3 sponsor accounts
77 | T0077/QA/T0075/D | QA | Student 4 | Tester | Test feature formally | T0075/D | 2026-02-23 11:00 | 2026-02-23 11:30 | Completed | 0.5 | 0.5 | 15 | 15
78 | T0078/D | Development | Student 4 | Developer | Implement feature |  | 2026-02-16 | 2026-03-19 | Completed | 2 | 3.5 | 50 | 87.5 | Functional: List and display published sponsorships and donations
79 | T0079/D | Development | Student 4 | Developer | Test feature informally | T0078/D | 2026-03-19 17:00 | 2026-03-19 18:00 | Completed | 1 | 1 | 25 | 25
80 | T0080/QA/T0078/D | QA | Student 4 | Tester | Test feature formally | T0078/D | 2026-03-19 18:00 | 2026-03-19 19:00 | Completed | 1 | 1 | 30 | 30
81 | T0081/D | Development | Student 4 | Developer | Implement feature |  | 2026-02-28 19:00 | 2026-03-11 13:00 | Completed | 2 | 4 | 50 | 100 | Functional: CRUD for sponsorships and their donations
82 | T0082/D | Development | Student 4 | Developer | Test feature informally | T0081/D | 2026-03-11 13:00 | 2026-03-11 14:00 | Completed | 1 | 1 | 25 | 25
83 | T0083/QA/T0081/D | QA | Student 4 | Tester | Test feature formally | T0081/D | 2026-03-11 14:00 | 2026-03-11 15:00 | Completed | 1 | 1 | 30 | 30
84 | T0084/D | Development | Student 4 | Developer | Implement feature |  | 2026-03-11 16:30 | 2026-03-15 12:00 | Completed | 2 | 3 | 50 | 75 | Logic for publishing sponsorships and immutability
85 | T0085/D | Development | Student 4 | Developer | Test feature informally | T0084/D | 2026-03-15 12:00 | 2026-03-15 13:00 | Completed | 1 | 1 | 25 | 25
86 | T0086/QA/T0084/D | QA | Student 4 | Tester | Test feature formally | T0084/D | 2026-03-15 13:00 | 2026-03-15 14:00 | Completed | 1 | 1 | 30 | 30 | Formal testing of sponsorship publishing and sponsor workflows
87 | T0087/D | Development | Student 4 | Developer | Customise the starter |  | 2026-03-19 19:00 | 2026-03-19 20:30 | Completed | 1.5 | 1.5 | 37.5 | 37.5 | UI Internationalisation (EN/ES) for sponsorship-related views
88 | T0088/D | Development | Student 5 | Developer | Customise the starter |  | 2026-02-05 09:30 | 2026-02-05 10:00 | Completed | 0.5 | 0.5 | 12.5 | 12.5 | Edit Logo.png and Title fragments
89 | T0089/D | Development | Student 5 | Analyst | Create domain model |  | 2026-02-05 10:00 | 2026-02-15 10:00 | Completed | 2 | 4 | 80 | 160 | Implement data model sketched in Model-05.uxf
90 | T0090/D | Development | Student 5 | Developer | Implement feature |  | 2026-02-10 18:00 | 2026-02-10 23:30 | Completed | 2 | 5.5 | 50 | 137.5 | Functional: Acquire auditor role and update profile
91 | T0091/D | Development | Student 5 | Developer | Test feature informally | T0090/D | 2026-02-16 17:30 | 2026-02-23 11:00 | Completed | 1 | 2 | 25 | 50 | Create sample data for 3 auditor accounts
92 | T0092/QA/T0090/D | QA | Student 5 | Tester | Test feature formally | T0090/D | 2026-02-23 11:00 | 2026-02-23 11:30 | Completed | 0.5 | 0.5 | 15 | 15
93 | T0093/D | Development | Student 5 | Developer | Implement feature |  | 2026-02-16 | 2026-03-19 | Completed | 2 | 3.5 | 50 | 87.5 | Functional: List and display published audit reports and sections
94 | T0094/D | Development | Student 5 | Developer | Test feature informally | T0093/D | 2026-03-19 17:00 | 2026-03-19 18:00 | Completed | 1 | 1 | 25 | 25
95 | T0095/QA/T0093/D | QA | Student 5 | Tester | Test feature formally | T0093/D | 2026-03-19 18:00 | 2026-03-19 19:00 | Completed | 1 | 1 | 30 | 30
96 | T0096/D | Development | Student 5 | Developer | Implement feature |  | 2026-02-28 19:00 | 2026-03-11 13:00 | Completed | 2 | 4 | 50 | 100 | Functional: CRUD for audit reports and their sections
97 | T0097/D | Development | Student 5 | Developer | Test feature informally | T0096/D | 2026-03-11 13:00 | 2026-03-11 14:00 | Completed | 1 | 1 | 25 | 25
98 | T0098/QA/T0096/D | QA | Student 5 | Tester | Test feature formally | T0096/D | 2026-03-11 14:00 | 2026-03-11 15:00 | Completed | 1 | 1 | 30 | 30
99 | T0099/D | Development | Student 5 | Developer | Implement feature |  | 2026-03-11 16:30 | 2026-03-15 12:00 | Completed | 2 | 3 | 50 | 75 | Logic for publishing audit reports and immutability
100 | T0100/D | Development | Student 5 | Developer | Test feature informally | T0099/D | 2026-03-15 12:00 | 2026-03-15 13:00 | Completed | 1 | 1 | 25 | 25
101 | T0101/QA/T0099/D | QA | Student 5 | Tester | Test feature formally | T0099/D | 2026-03-15 13:00 | 2026-03-15 14:00 | Completed | 1 | 1 | 30 | 30 | Formal testing of audit report publishing and auditor workflows
102 | T0101/D | Development | Student 5 | Developer | Customise the starter |  | 2026-03-19 19:00 | 2026-03-19 20:30 | Completed | 1.5 | 1.5 | 37.5 | 37.5 | UI Internationalisation (EN/ES) for audit-related views
103 | T0102/O | Other | Student 1 | Operator | Package deliverable |  | 2026-03-20 15:00 | 2026-03-20 21:00 | Completed | 3 | 6 | 90 | 180
104 | T0103/R | Revision | ALL | Tester | Check deliverable |  | 2026-03-20 21:00 | 2026-03-20 22:00 | Completed | 1 | 1 | 30 | 30
105 | T0104/O | Other | Student 1 | Operator | Upload deliverable |  | 2026-03-20 22:00 | 2026-03-20 23:00 | Completed | 1 | 1 | 30 | 30

## D02
Deliverable D02
Use this form to document the tasks that you perform in your projects. Please, review the colour code in the "Abstract" sheet. In the exceptional case that you need to perform more tasks than expected, add them at the end.
| Costs | Expected: | 1795
|  | Actual: | 1855
[7 empty] | Execution period |  |  | Workload (in hours) |  | Costs (in EUR)
ORDER | ID | Type | Assignee | Role | Activity | Parent | Start moment | End moment | Status | Expected | Actual | Expected | Actual | Description
1 | T0001/O | Other | ALL | Student | Attend lecture |  | 2026-04-06 10:40 | 2026-04-06 12:30 | Completed | 1.8333 | 1.8333 | 0 | 0 | L04 – Formal testing, S01 – Functional testing
2 | T0002/O | Other | ALL | Student | Attend lecture |  | 2026-04-09 08:30 | 2026-04-09 10:40 | Completed | 1.8333 | 1.8333 | 0 | 0 | L04 – Formal testing, S02 – Performance testing
3 | T0003/O | Other | ALL | Student | Attend lecture |  | 2026-04-13 10:40 | 2026-04-13 12:30 | Completed | 1.8333 | 1.8333 | 0 | 0 | Follow up
4 | T0004/O | Other | ALL | Student | Attend lecture |  | 2026-04-16 08:30 | 2026-04-16 10:40 | Completed | 1.8333 | 1.8333 | 0 | 0 | L04 – Formal testing, S03 – Advanced topics
5 | T0005/O | Other | ALL | Student | Attend lecture |  | 2026-04-20 10:40 | 2026-04-20 12:30 | Completed | 1.8333 | 1.8333 | 0 | 0 | Follow up
6 | T0006/O | Other | ALL | Student | Attend lecture |  | 2026-04-27 10:40 | 2026-04-27 12:30 | Completed | 1.8333 | 1.8333 | 0 | 0 | Follow up
7 | T0007/O | Other | ALL | Student | Attend lecture |  | 2026-04-30 08:30 | 2026-04-30 10:40 | Completed | 1.8333 | 1.8333 | 0 | 0 | Assessments
8 | T0008/O | Other | ALL | Student | Attend lecture |  | 2026-05-04 10:40 | 2026-05-04 12:30 | Completed | 1.8333 | 1.8333 | 0 | 0 | Assessments
9 | T0009/O | Other | ALL | Student | Update charter & risks |  | 2026-04-07 16:00 | 2026-04-07 18:00 | Completed | 2 | 2 | 0 | 0 | Review methodology, commit to Level B, and conduct risk analysis.
10 | T0010/A | Analysis | Student 4 | Analyst | Rewrite requirements |  | 2026-04-08 10:00 | 2026-04-10 14:00 | Completed | 6 | 6 | 240 | 240 | Structured specification of B/1 to B/6 (Functional & Non-functional).
11 | T0011/A | Analysis | Student 4 | Analyst | Draft analysis document |  | 2026-04-09 10:00 | 2026-04-13 12:00 | Completed | 4 | 4 | 160 | 160 | Document doubts, inconsistencies, and list of questions for lecturers.
12 | T0012/A | Analysis | Student 2 | Analyst | Create domain model |  | 2026-04-11 16:00 | 2026-04-16 19:00 | Completed | 8 | 8 | 320 | 320 | Preliminary UML model for Manager, Projects and components (B/1, B/2).
13 | T0013/A | Analysis | Student 2 | Analyst | Create domain model |  | 2026-04-14 10:00 | 2026-04-18 13:00 | Completed | 5 | 5 | 200 | 200 | UML for Dashboards, PMs calculation (B/3), Sponsorships (B/4), and Ads (B/5).
14 | T0014/D | Development | Student 2 | Developer | Setup workspace |  | 2026-04-17 16:00 | 2026-04-18 20:00 | Completed | 4 | 4 | 100 | 100 | Establish shared workspace and configure initial Linting rules.
15 | T0015/QA | QA | Student 4 | Tester | Draft testing plan |  | 2026-04-20 10:00 | 2026-04-23 14:00 | Completed | 5 | 5 | 150 | 150 | Define testing requirements and prepare the baseline for the Testing report.
16 | T0016/D | Development | Student 2 | Developer | Implement feature |  | 2026-04-22 16:00 | 2026-04-26 20:00 | Completed | 6 | 6 | 150 | 150 | Early code structure/prototype for Manager role and Ad Banners CRUD.
17 | T0017/D | Development | Student 2 | Developer | Implement feature |  | 2026-04-25 10:00 | 2026-04-29 14:00 | Completed | 6 | 6 | 150 | 150 | Prototype for Project entities and components (Inventions, Campaigns).
18 | T0018/R | Revision | Student 4 | Analyst | Compile reports |  | 2026-04-30 10:00 | 2026-05-02 14:00 | Completed | 4 | 4 | 160 | 160 | Integrate UML and requirements into the final Analysis and Planning reports (B/6).
19 | T0019/QA | QA | Student 4 | Tester | Compile technical reports |  | 2026-05-01 16:00 | 2026-05-03 19:00 | Completed | 3 | 3 | 90 | 90 | Generate and review final Lint report and Testing report (B/6).
20 | T0020/O | Other | Student 4 | Operator | Package deliverable |  | 2026-05-08 16:00 | 2026-05-08 23:00 | Ongoing | 2 | 4 | 60 | 120 | Final check of all required D02 documents and zip creation.
21 | T0021/O | Other | Student 4 | Operator | Upload deliverable |  | 2026-05-08 23:00 | 2026-05-08 23:30 | Planned | 0.5 | 0.5 | 15 | 15 | Upload the final deliverable to the platform.

## D03
Deliverable D03
Use this form to document the tasks that you perform in your projects. Please, review the colour code in the "Abstract" sheet. In the exceptional case that you need to perform more tasks than expected, add them at the end.
| Costs | Expected: | 0
|  | Actual: | 0
[7 empty] | Execution period |  |  | Workload (in hours) |  | Costs (in EUR)
ORDER | ID | Type | Assignee | Role | Activity | Parent | Start moment | End moment | Status | Expected | Actual | Expected | Actual | Description
1 | T0001/O | Other | ALL | Student | Attend lecture |  | 2026-05-07 08:30 | 2026-05-07 10:40 | Completed | 1.83 | 1.83 | 0 | 0 | L05 – Miscellaneous topics, S01 – Workshop
2 | T0002/O | Other | ALL | Student | Attend lecture |  | 2026-05-11 10:40 | 2026-05-11 12:30 | Planned | 1.83 | 1.83 | 0 | 0 | Workshop Presentations
3 | T0003/O | Other | ALL | Student | Attend lecture |  | 2026-05-14 08:30 | 2026-05-14 10:40 | Planned | 1.83 | 1.83 | 0 | 0 | L05 – Miscellaneous topics, S02 – Advanced topics
4 | T0004/O | Other | ALL | Student | Attend lecture |  | 2026-05-18 10:40 | 2026-05-18 12:30 | Planned | 1.83 | 1.83 | 0 | 0 | Assessments
5 | T0005/O | Other | ALL | Student | Attend lecture |  | 2026-05-21 08:30 | 2026-05-21 10:40 | Planned | 1.83 | 1.83 | 0 | 0 | Assessments
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## Internal
Internal data
This sheet contains internal data that are used elsewhere to perform some checks and computations. Please, do not modify it al all.
Prospective assignees
Student 1
Student 2
Student 3
Student 4
Student 5
ALL
Statuses
Planned
Ongoing
Finished
Moments
2025-01-01
2100/31/12 23:59:59
Roles | Cost | Tasks…
Student | 0 | Attend lecture | Study and train | Attend work meeting | Other (Describe)
Manager | 50 | Make plans | Make re-plannings | Initialise repository | Supervise task | Write report | Other (Describe)
Analyst | 40 | Elicit requirements | Define features | Create domain model | Write report | Other (Describe)
Developer | 25 | Create dev. config. | Customise the starter | Implement feature | Test feature informally | Write report | Other (Describe)
Tester | 30 | Check deliverable | Check task | Test feature formally | Test performance formally | Write report | Other (Describe)
Operator | 30 | Prepare dep. platf. | Package deliverable | Upload deliverable | Deploy application | Keep application running | Write report | Other (Describe)
Other | 10 | Other (Describe)
Task types | Key
Management | M
Development | D
QA | QA
Revision | R
Other | O